## 2025-26
Everton Parish Council - Agenda Item Tracker
Ser | Item | Year | Date | Summary | Action | Update | Responsible | Target Date | Status
1 | 1761 | 2025 | 2025-10-06 | To seek community support for speed reduction within parish | Council to await NCC Cllr Mike Robinson's report on next steps. | To proceed with village petition as evidence of support. Article put in HEDS to kick off the process | Cllr Thomson | 2026-08-01 | Awaiting External Response
2 | 1762 | 2025 | 2025-10-06 | To award funding of £350 to Five Villages First Responders | Clerk to action payment and notify payee. |  |  |  | Complete
3 | 1763 | 2025 | 2025-10-06 | To award funding of £1500 to Metcalfe Recreation Committee | Clerk to action payment and notify payee. |  |  |  | Complete
4 | 1764 (2) | 2025 | 2025-10-06 | To object to PA 26/01010/FUL | Clerk to sumbit objection to BDC Planning |  |  |  | Complete
5 | 1764 (3) | 2025 | 2025-10-06 | To comment upon 25/00655/HSE | Clerk to sumbit comments to BDC Planning |  |  |  | Complete
6 | 1768/e | 2025 | 2025-10-06 | The council discussed waste bin provision in the parish and would engage with BDC Waste Management to increase the number of waste bins | Cllr Waddington would engage with BDC | Following two separate visits to the village, BDC have stated they will; remove the Paddock bin and put a replacement at the corner of Church Street and Chapel Lane; place a new bin on Chapel Lane by the entrance to the Blacksmiths; and put a new bin at the jct of Harwell Sluice Lane and Middle Cross Lane. Previously used town centre bins have been placed on Chapel Lane and the jct of Harwel Sluice and Middle Cross lanes. These will be repainted. The bin from Pinfold Lane has been relocated to the jct Church Street and Chapel Lane. A rpelacement bin for Pinfold Lane is being sourced. Bins have been refurbished and painted. | Cllr Waddington | 2026-02-28 | Ongoing
7 | 1794 1810 | 2025 2026 | 1/12/25 5/01/26 | Kissing Gate Disrepair Kissing Gate Repair quotes recived appear excessive | Resolved to obtain three quotes Cllr Wiles to seek partial repair price | Cllr Thomson stated that if no reasonable quote was received then he would propose to build a new gate at cost | Cllr Waddington | 2026-03-31 | Ongoing
8 | 1795 | 2025 | 2025-12-01 | Clerk Salary LGA Pay Award | Resolved to agree 3% LGA increase and SCP Increment |  |  |  | Complete
9 | 1796 | 2025 | 2025-12-01 | Draft Budget agreed, 24, 534 precept, 5.45 Band D | Clerk to submit precept demand to BDC |  |  |  | Complete
10 | 1799/d 1814/f | 2025 | 2025-12-01 | Rural Crime Scheme Training | To advertise and support RCW Scheme in Everton and Harwell | All Cllrs requested to attend Successful event. 5 new wardens signed up | Cllr Troop | 2026-01-20 | Complete
11 | 1799/e 1814 | 2025 2026 | 01/12/25 05/01/26 | ENP - Consultation Update | To move to Key Stage 2 | To proceed with draft rewrite. Meeting held between Chair and Cllr Upton to discuss hierachy of EPC Plan and ENP | Cllr Upton | 2026-03-31 | Ongoing
12 | 1797 | 2025 | 2025-12-01 | Approve Metcalfe Trust TOR | Chair to present copy for signature | Signed and lodged with Clerk | Cllr Thomson |  | Complete
13 | 1800b | 2025 | 2025-12-01 | Accept Memorial Bench Gift | Clerk to add memorial bench to asset register |  |  |  | Complete
14 | 1812/a | 2026 | 2026-01-05 | Apply for MT Grant | Cllr Thomson to apply for MT grant | MRC approved a £1541 Amenity Grant at their meeting on the 26 Jan 2026 | Cllr Thomson | 2026-02-28 | Complete
15 | 1813/c | 2026 | 2026-01-05 | Enforcement update was not available as Cllr Pashley was unavailable | Create an Enforcement tracker to provide accurate oversight of all ongoing enforcement cases | Cllr Thomson to arrange a meeting with enforcement and Cllr Pashley, specifically about Mill Lane | Cllr Wright Support PC Clerk | Monthly | Ongoing
16 | 1814/c | 2026 | 2026-01-05 | Use of EPC official councillor emails | All councillors to activate and use for all PC business their allocated email | New communications policy adopted on 2 Feb 2026 | Cllr Thomson | 2026-03-02 | Complete
17 | 1814/f | 2026 | 2026-01-05 | Everton Respect campaign outlined | To promote monthly theme to build community cohesion | Agreed to tie it to the PC year starting May 2026 with the exception of the bi-annual litter pick | Cllr Waddington Support Cllr Thomson | 2026-05-01 | Ongoing
18 | 1814/f | 2026 | 2026-01-05 | Village litter sweep | To hold village litter sweep as part of the Keep Britain Tidy campaign in March. | To try and get involvement by the school and MT and MRC | Cllr Waddington Support Cllr Wiles | 2026-03-29 | Ongoing
19 | 1816 | 2026 | 2026-01-05 | White Post Box dedication | A suitable date will be identified to conduct the dedication | To involve school and church | Cllr Waddington Support Cllr Wiles | 2026-04-30 | Ongoing
20 | 1816 | 2026 | 2026-01-05 | War Memorial Rededication | A suitable date will be identified to conduct the rededication | To involve school and church | Cllr Wiles | 2026-04-30 | Ongoing
21 | 1821 | 2026 | 2026-02-02 | The issue of enforcement on Mill Lane was raised again by a member of the public. | To hold a meeting with enforcement and Cll Pashley. Linked to Ser 15 | Email sent to Cllr Pashley | Cllr Wright Support Cllr Foster | 2026-02-28 | Ongoing
22 | 1823 | 2026 | 2026-02-02 | Public consultation on West Burton STEP Fusion project | To engage local PCs to create aJoint Parish Action Group | Cllr Thomson has reached out to all concerned PCs in our area | Cllr Thomson | 2026-02-28 | Ongoing
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
| 0 | 2025 | 2026-01-01 | Dummy Item - Deferred |  |  |  |  | Deferred
| 0 | 2025 | 2026-01-01 | Dummy Item - Cancelled |  |  |  |  | Cancelled
| 0 | 2025 | 2026-01-01 | Dummy Item - Awaiting External Action |  |  |  |  | Awaiting External Action
| 0 | 2025 | 2026-01-01 | Dummy Item - Awaiting External Response |  |  |  |  | Awaiting External Response
| 0 | 2025 | 2026-01-01 | Dummy Item - Duplicate | Duplicate / Tracked Elsewhere
| 0 | 2025 | 2026-01-01 | Dummy Item - Cancelled |  |  |  |  | Cancelled
| 0 | 2025 | 2026-01-01 | Dummy Item - Complete |  |  |  |  | Complete